## Sheet1
ID | Task | Predecessors | Resources | Duration | 2017-01-09 | 2017-01-10 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-14 | 2017-01-15 | 2017-01-16 | 2017-01-17 | 2017-01-18
1 | Discussing the problem |  | 4 | 2 hours | 4
2 | Finding a solution |  | 4 | 2 hours | 4
3 | Solve obstacle course with SMR-CL in simulator | 1,2 | 2 | 2 days | 2 | 2
4 | Calibrating sensors |  | 2 | Continuous
5 | Basic movement commands in C |  | 2 | 2 days | 2 | 2
6 | Implement the C script in the simulator | 1,2 | 2 | 2 days |  |  | 2 | 2
7 | Implement SMR-CL with real robot | 3,4 | 2 | 2 days |  |  | 2 | 2
8 | Implement C with real robot | 3,4,5,6 | 2 | 2 days |  |  |  |  | 2 |  |  | 2
9 | Work on poster |  | 2 | 2 days |  |  |  |  | 2 |  |  | 2
10 | Testing SMR-CL and C on simulator course | 3,5,6 | 4 | 1 day | [8 empty] | 4
11 | Testing SMR-CL and C on final course | 7,8 | 4 | 1 day | [9 empty] | 4